Media Services Transition Checklist

Changing your media agency can be perceived as overwhelming.  This outline provides a checklist by which to track the various tasks associated with such a transition.

Over-communication is key!

Experience has proven that assigning a transition team at the agency should be the first step. This transition team will be tasked with discovery — meaning collecting all relevant information from CLIENT and your vendors. This includes current processes, active assignments, roles and responsibilities across media and marketing, goals, previous results.  We facilitate vendor communication and collect overall requirements. A transition team will be provided in all necessary geographies.

With the transition team at work on-boarding the business, your core agency team can focus on your business.

First 30 Days

- Immediately assemble the transition teams for various geographies and media channels. Set transition timeline in collaboration with CLIENT

- Align on assignments and success metrics

- Communication objectives

- High level communication flowcharts

- Strategic imperatives

- KPI’s

- Roles and responsibilities

- Savings/value objective

- Electronically share files

- Historical and current media plans

- Target audience analysis

- Strategy presentations

- Competitive information

- Develop technology solutions in collaboration with CLIENT to automate workflow

- Transition with current agencies if applicable in all necessary geographies

- Planning responsibilities

- Negotiating & buying responsibilities

- Billing turnover date

- Establish bill-pay process

First 60 Days

- Metrics Workshop

- Review of historical campaign performance results, define key conversion events, establish metric goals, etc.

- Define tracking and measurement scope of work (data collection needs, definition of Web pages to be tracked, system integrations, any data matching, etc.)

- Geographic Coordination

- Weekly calls / teleconferences

- Weekly / bi-weekly status report review

- CLIENT and AGENCY representatives visit key geographies, as appropriate, to review transition status

- Bring agreed technology solutions online

- Load historical media data

- Introduce relevant CLIENT data

- Sync with relevant existing visualization technologies

First 30 Days – Media Partners

- Transition Television buys

- Buying and program guidelines and restrictions

- Sales rep contact lists

- Copies of current year contracts including unit rates and rating estimates, re-confirmed by stations

- Transfer/input into the relevant local system

- Detail of pending or active buys & immediate buy transfer to AGENCY

- Projected cost-per-points for current year

- Added-value properties: placed and to be placed

- Identification of special buys: sponsorships, corporate commitments, licensing agreements, grandfather deals, multi-year deals, multi-media, etc.

- Historical buys, buy input and posts

- Outstanding ADU’s, make-goods to be placed

- Establish traffic procedures and reports

- AGENCY to establish any credit requirements with partners

- Transition Radio buys

- Follow the same steps as detailed in the Television transition

- Transition Magazine

- Letters to publishers from client advising agency change and effective date (AGENCY to provide draft)

- List of current primary sales contact representatives

- Copies of current year buys

- Detail of pending or active buys

- Copies of current year print contracts– Contract fulfillment, paging and short-rate status

- Identification of special buys/needs: sponsorships, corporate commitments, licensing agreements, grandfather deals, multi-year deals, multi-channel

- Historical buys & positioning and content guidelines review

- Status of circulation audits

- AGENCY to establish any credit requirements with partners

- Establish digital terms

- Copies of current year buys and contracts

- Detail of pending or active buys and contracts

- Added-value summary: placed and to be placed

- Identification of special buys: corporate commitments, grandfather deals, multi-year deals, multi-media, franchise positions, etc.

- Historical buys and performance analysis

- Identify desired post-click activities

- Identify methodology for tracking post-click activities

- AGENCY terms (not already in place) to be completed with any partners

- Transition outdoor plans

- Copies of current year buys and contracts

- Existing site location maps

- Detail of pending or active buys and contracts

- Transfer/input into the relevant local system

- Added-value summary: placed and to be placed

- Identification of special buys: corporate commitments, grandfather deals, multi-year deals, multi-media, franchise positions, city ordinance details, etc.

- Historical buys and performance analysis

- Status of posting reports and market rides/audits

- Traffic and site location selection guidelines

- Establish traffic procedures

- AGENCY to establish any credit requirements with partners

First 30-60 Days – Media Partners

- Digital Transition

- Transition live buys (display & search)

- CLIENT to cancel IOs; cancellation windows are typically 30 days or less (unless it is custom digital work)

- AGENCY to re-issue IOs to keep desired online media and search media live

- Search Transition

- Acquire vendor account IDs for key publishers (Google, Yahoo, etc.)

- Define tracking requirements and linking strategy/landing pages

- Architect search campaigns to meet objectives